## Sprint Backlog
Sprint Backlog
| Sprint # | 1
Backlog Item | Task Name | Story Points | Responsible | Status | Estimated Efforts (in hours) | Remaining Efforts (in hours) | Remaining Efforts (in hours) | Remaining Efforts (in hours)
[5 empty] | Week 1 | Week 2 | Week 3 | Week 4
Making chat bot interactive |  | 10
Answer basic questions | Task a | 8 | Atanas Angelov | Done | 1 | 2 | 2 | 1
|  |  | Qrow Feng | Done | 0 | 0 | 0 | 0
Adding different language jokes | Task b | 2 | Tyler Mullings | Done | 3 | 2 | 1 | 3
Reccomendations |  | 4
Movies | Task c | 4 | Marian Finaru | Done | 2 | 3 | 1 | 2
Weather |  | 8
Implementing weather system | Task d | 8 | Evaldas Vainavicius | Done | 2 | 1 | 2 | 1
Online/Offline status |  | 2
Implementing online/offline status if user wants to know |  | 2 | Evaldas Vainavicius | Done | 0 | 2 | 1 | 2
Ideal Effort Hours |  |  |  |  | 8 | 5.3333 | 2.6667 | 0
Effort Remaining Hours |  |  |  |  | 8 | 10 | 7 | 9

## Sheet2
This sheet is to enable the drop-down lists
To Do | 1
Doing | 2
Done | 3
4